## Slide 1: OIR Committee Status Report
2nd face-to-face meeting
Oct. 12-13, 2014
Beckman Center of the National Academies
Irvine, CA

## Slide 2: Statement of Task
In order to best address the science objectives identified in the Decadal Surveys, and to help achieve the best science return from NSF investment in OIR astronomy over the next 10-15 years, the committee will:
Identify the principal capabilities that exist in the U.S. ground-based optical and infrared system--both federal and non-federal--and are critical to addressing the science objectives
Identify the most important additions and adjustments to the U.S. ground-based O/IR system that would best position it to address the science objectives

## Slide 3: In its work, the committee
will develop its own working definition of the U.S. OIR system
will consider instrumentation, data management, and support capabilities (incl. training, and sustaining expertise) alongside observational capabilities
will focus on achieving science outcomes for LSST and non-LSST decadal priorities
will consider what coordination is needed

## Slide 4
Weekly telecons (13 so far)
First face-to-face meeting July 2014; discussions with NSF, DOE, NASA, OSTP, STScI, NRAO, ESO
Technical and demographic information requested from 24 public and private observatories; received 80% to date (deadline was Sept 29)
Background material written for report (current science, observatories, training, and sustaining expertise); start of summary of needs
White Papers and comments requested from community; 38 WP from 317 authors + 3 comments received to date (advertised on NRC, AAS webpages; Astronomers facebook 4 times; AAS and NOAO exploders; Nature news interview)
Work Status

## Slide 5: Upcoming work
Continue weekly telecons to formulate conclusions and recommendations, and continue discussions on White Papers
Continue to receive White Papers till December
Continue report writing
Dec. 2-3 – final face-to-face meeting, Washington DC
Mid-January – finalize draft
Late January – submit report to NRC for external review
Feb.-April – revise report after comments received
April – release report to NSF and the public

## Slide 6
In open sessions:
Discuss future plans and the OIR System outlook with federal and private observatory directors
Hear from data management experts
Hear from AO experts
Discuss White Papers received
Hear from community
Discuss report guidelines with NSF and public
In closed sessions:
Review guiding principles
Discuss conclusions and possible recommendations
Discuss other input needed
Decide on speakers for December face-to-face meeting
Agree on writing assignments for report
Goals this meeting

## Slide 7: End Game
Ultimately, our report should have actionable recommendations that enable the best science by helping to unite the System in a way that makes it greater than the sum of its parts.