## Slide 1
ITER Engineering Science and Breakthroughs
Gyung-Su Lee
Chief Operating Officer / DDG

## Slide 2: Outline
Background : Change and Reform
Staged Approach : First Plasma to DT Operation
Building and Plant Construction
Critical Components and Systems Manufacturing
Advancement of Technology R&D Area
Technology & Engineering Breakthroughs and Spinoffs
Summary

## Slide 3
Action Plan 2015: Set clear priorities & timeline for reform
Reorganized and Integrated ITER Central Team (IO-CT) with Domestic Agencies
  Clear decision processes and accountability
  Executive Project Board, Reserve Fund, Project Teams
Finalized and stabilized ITER critical component design
Comprehensive integrated bottom-up review of all activities, processes and systems
  Developed an optimized resource-loaded schedule for timely, cost-effective construction and operation through D-T plasma. Updated the 2010 Baseline (Baseline2016).
Developed and promoted a strong, organization-wide nuclear project culture
Background : Change and Reform

## Slide 4
Extensive works among IO and DAs to finalize revised baseline: Baseline2016 Schedule and Cost (OPS & OPC)
Schedule and resource estimates through First Plasma (2025) consistent with Members’ budget constraints
Adopted 4-stage approach through Deuterium-Tritium Operation (2035) consistent with Members’ financial and technical constraints
Staged Approach : FP to DT Operation

## Slide 5
Start Machine Assembly Phase I
Cryostat Closed
TF Coils (1.1.P1B.JA.01)
Central Solenoid (1.1.P4A-4B.US.01)
1st Plasma
Level 0 Construction Schedule to First Plasma in 2025
ITER CONSTRUCTION AND OPERATIONS (00.01/00.02)
Major ITER Milestones
Start Lower Cryostat Assembly
VV Sector 05,04,03, 02, 09
Lower Cryostat Assembly Completed
Start Machine Assembly Phase I
First CS Module CSL3 Last CS Module CSU3
1st Plasma
TF Coils (1.1.P1A.EU.01)
Vacuum Vessel (1.5.P1A.EU)
Building Construction (6.2.P2.EU.05)
Construction
(2.2.P1.IO)
TF Coils 12,13, 08, 10,02,16, 07, 15
VV Sector
Sub-Assembly Completed
VV Sector Assembly Completed
Cryostat Closed
(Install Bioshield Lid)
End Machine Assembly Phase I
PF Coils 05,06,02, 04, 01 03
Poloidal Field Magnets
58
TF Coils 06,09,11, 05,03, 01,04,17,14,18
Start VV Sectors Sub-Assembly
VV Sector 06 01(07)
Vacuum Vessel (1.5.P1A.KO)
Assembly Bldg 13 RFE 1A
Bldg 11 RFE 1B Stage 1
Operations
Vacuum Vessel (1.5.P1A.IO)
VV Sector 08 07(01)
Bldg 11 RFE1B Stage 2
2016
2017
2018
2019
2020
2021
2022
2023
2024
2025
Start VV Sector 08 Sub-Assembly
Start Cryostat Base Installation
Assembly Milestone Schedule to First Plasma
Start Integrated Commissioning I

## Slide 6
Building & Plant Construction
11 TOKAMAK BUILDING
13 ASSEMBLY BUILDING
14 TRITIUM BUILDING
15 RF HEATING BUILDING
17 CLEANING FACILITY BUILDING
19 SEISMIC ISOLATION BASEMAT
21 HOT CELL BUILDING
23 RAD WASTE BUILDING
24 PERSONNEL ACCESS CONTROL BUILDING
32 MAGNET POWER CONVERSION BUILDING 1
33 MAGNET POWER CONVERSION BUILDING 2
34 NB POWER SUPPLY BUILDING
36 MAIN ALTERNATING CURRENT DISTRIBUTION BLDG
37 NB HIGH VOLTAGE POWER SUPPLY BUILDING
38 REACTIVE POWER CONTROL BUILDING
44 45 EMERGENCY POWER SUPPLY BUILDING
46 47 MEDIUM VOLTAGE DISTRIBUTION BUILDING
49 RTE CONTROL BUILDING
51 CRYOPLANT COMPRESSOR BUILDING
52 CRYOPLANT COLDBOX BUILDING
55 PF COIL FABRICATION BUILDING
56 CRYOSTAT ASSEMBLY BUILDING
57 58 SIC GENERATOR BUILDING
59 60 IP GENERATOR BUILDING
61SITE SERVICES BUILDING
62 HOT WATER BOILERS BUILDING
67 COLD BASIN & COOLING TOWERS
68 COOLING WATER PUMP STATION
71 CONTROL BUILDING
74 DIAGNOSTICS BUILDING
75 FD & SWITCHING NETWORK RESISTOR BLDG

## Slide 7
Tokamak Building B11
Tritium Building B14
Diagnostic Building B74
Integrated Building Design
Construction Design
Execution Design & Construction
As-Built Design
1
2
3
4
Tokamak Complex Design & Construction
* Design Interface fully FROZEN and no more PCRs affecting Tokamak Building.
L3
L2
L1
B1
B2
L4
L5
Roof

## Slide 8
Status of Tokamak Complex Design & Construction
Construction Design
Execution
Design &
Construction
Level B2 Slab
Level B2 Walls / B2M
Level B1
Bldg. 11, 14, 74: September 2017 (Approved by IO)
Level L2
Roof
Bldg. 11, 14: October 2017 (1st issue)
Bldg. 74: August 2016 (1st issue)
Level L1
Level L3
Level L4
Bldg. 11, 14 : August 2016 (1st issue)
Bldg. 11, 14, 74: August 2017 (last version)
Level L5
Bldg. 11, 14: May 2017 (1st issue)
Bldg. 11, 74: January 2018
Level B2
Categorization
Level
Building / MRR Acceptance Reports approval dates
As Built Design
4
3
2

## Slide 9
Tokamak Complex

## Slide 10
Bioshield Concrete Works Completed

## Slide 11
Worksite 1 (TKM Assembly)
Worksite 2
Worksite 3
Worksite 4
Worksite 5 (SSEN)
Worksite 5 (PPEN)
15
14
21
Worksite 1: Tokamak Main Machine, Worksite 2: Tokamak Complex Plant + RF Bldg.(B15)
Worksite 3: Hot Cell + Rad Waste + Control Buildings, Worksite 4: Cryogenic Plant + Cooling Station
Worksite 5: Electrical & Power Supply Buildings,
Construction-by-Area Approach (Worksites)

## Slide 12
Bio-shield
Port Cell
Gallery
In-vessel
In-cryostat
Port & Cryostat
B1 Port Cell
L1 Port Cell
L2 Port Cell
L3
L4
L5
B2 Tokamak Interface
B2
B1
L1
L2
①
②
③
④
⑤
❶
❷
❸
❹
❺
Cryostat
(Tokamak Pit)
Gallery
Port Cell
Bio-shield
CTTA (Worksite 1) & CTTC (Worksite 2)
IO CTTC Contracts and EU-DA Building Services (TB04)
Contract
Co-activity
Area

## Slide 13
Tokamak Assembly Flow (B17 - B13 - B11)
Introduction of the Tokamak components in Building 17;
Preparation and sub-assembly of the sectors in Building 13;
Transport of the sector sub-assemblies via 2x750t crane to the Tokamak Pit;
Final assembly of the components/sub-assemblies in the Tokamak Pit.

## Slide 14
Tokamak Lower In-pit Installation Activities
Tokamak Assembly Hall Activities
Tokamak In-Pit Installation Activities
Learning Curve with Sectors 6 & 7
Sub-assembly
Sector-by-Sector Assembly (KSTAR, EAST, JT-60SA) with Learning Curve by Sectors 6 & 7

## Slide 15
Tokamak Assembly Tools Design
Sector Sub-Assembly Tool (SSAT)
Sector Lifting Tool

## Slide 16
Sector Sub-Assembly Tool (SSAT #1)
B13 Assembly Building

## Slide 17
Sector Sub-Assembly Tool (SSAT #2)
RH/LH Horizontal Beam
(IB) Support Block
(OB) Support Block

## Slide 18
One-of-Kind Plant : Cryogenic System
ITER variable heat loads
(overall heat loads)

## Slide 19: In-kind Procurement Manufacturing
Toroidal Field coils (18)
Poloidal field coils (6)
Cryostat
Thermal shield
Vacuum vessel
Blanket modules
Feeders (31)
Divertor
Central solenoid (6)
Correction coils (18)

## Slide 20: Vessel Systems in Mass Production
Cryostat, Thermal Shields,
and Vacuum Vessel Sectors & Ports

## Slide 21
Lid
Lower Cylinder
Upper Cylinder
Base Section
Cryostat in Mass Production

## Slide 22
Thermal Shield in Mass Production

## Slide 23
Nuclear licensing as an ESPN (First In-Kind of Fusion Nuclear Pressure Vessel)
  The ITER VV is defined as an ESPN (Equipement Sous Pression Nucléaire) component that requires that all documents related to design, manufacturing, installation, and operation shall be reviewed and approved by an Agreed Notified Body (ANB) on behalf of the French Nuclear Authority (Autorité de Sûreté Nucléaire : ASN). → (Originally designed as a non-nuclear engineering (French nuclear regulation applied after site selection))
1st application of the RCC-MR 2007 Edition (Code & Standard)
  As main C&S, we are applying the RCC-MR 2007 Edition that is the first application on the ITER VV construction that cause a few of major updating of C&S itself during design and manufacturing.
Many clients (Complex interfaces)
  The VV supports many in vessel systems such as Blankets, Diverters, Diagnostics, In-vessel Coils, Port Plugs, Components of Heating and Current Drivers, Fuelling, Cooling Pipes, and Assembly, etc. Many of functional and physical interfaces cause long discussion because of mainly different design maturity of each system.
  → Main technical challenges have been resolved during manufacturing process
  → All 9 VV sectors are under manufacturing and the first sector (S#6) has been achieved ~77 % of progress
Vacuum Vessel in Full Production

## Slide 24
PS4
PS1
PS3
Upper Port
VV#6-PS1 : Completion of manufacturing (IC-23) with meeting all required tolerance
Delivered
from MDT (RF)
to HHI (KO)
PS2
Lower Port
Manufactured
by HHI (KO)
Status of VV Production in KO
PS : Poloidal Segment

## Slide 25
PS4
PS1
Upper Port
PS2
PS3
Lower Port
Status of VV Production in EU

## Slide 26: Superconducting Magnets in Full Production
TF Winding Pack, TF Structure, PF Coils, CS Coils, and CC-Coils

## Slide 27
Status of TF WP Production in JA

## Slide 28
Status of TF WP Production in EU
TF06
TF09
TF11 (arrived for insertion)
TF WP Instrumentation Test

## Slide 29
Status of TFCS Production
1) Root Gap : 0.5±0.25mm
2) Misalignment of Welding Root : Within±0.3mm
3) Matching the Splice Plate Side : Within ± 1.3mm

## Slide 30
Status of TF Insertion Process

## Slide 31
Two PF5 Real Double Pancakes (DPs) (DP7 and DP8) windings have been completed
PF5: 2nd DP(DP8) Winding Completed
Status of PF5 Production

## Slide 32
Five PF6 Real DPs(DP5, DP6, DP7, DP8 and DP9) windings have been completed
PF6: 2nd DP(DP8) VPI Completed
PF6: 3rd DP(DP7) VPI Under Preparation
Status of PF6 Production

## Slide 33
Five PF1 Real DP windings have been completed and the 5th DP is underway
PF1: 3rd DP VPI Completed
PF1: 5th DP Winding Underway
Status of PF1 Production

## Slide 34
Status of CS Coil Production
CS Module-1

## Slide 35: In-Vessel Components, Systems in Engineering and Production
W-Divertor, Be First Wall, Shield Blocks, and In-Vessel Coils

## Slide 36
Status of Blanket System
Main Functions of ITER Blanket System:
Exhaust the majority of the plasma power
Contribute in providing neutron shielding to superconducting coils
Provide limiting surfaces that define the plasma boundary during startup and shutdown

## Slide 37
Status of Blanket FW Manufacturing
RH access
Plasma
Exaggerated shaping

## Slide 38
Status of W-Divertor
Divertor Main Functions :
Minimize the helium and impurities content in the plasma
Exhaust part of the plasma thermal power

## Slide 39
Status of W-Divertor Manufacturing

## Slide 40
Status of In-Vessel Coil System
ELM coils (3 per sector)
Upper VS Coil
Lower VS Coil
Feeders
Feedthroughs
The in-vessel coils comprise: 3 x 9 picture-framed, ELM coils (aimed at controlling Edge Localized Modes) and 2 ring, VS coils (aimed at controlling Vertical Stability).
* PDR finalized successfully.

## Slide 41
Status of In-Vessel Coil Conductor
Round conductor with MgO ceramic insulation
Coils attachment through brackets
Unit lengths: up to 70 m
Weight: 12.4 kg/m
[Dimensions in mm]
[ASIPP]

## Slide 42
Status of In-Vessel Coil Engineering
Support Structure
Joints (to feeders)
2 Jumper Clamps
(Power Supply)
2 Insulating Breaks
2 Bellows
2 Pipes
(Cooling Supply)
IVC In-situ Joint
IVC FT & IB

## Slide 43: Advancement of Technology R&D
Heating & Current Drive Systems, Diagnostics, Remote Handling Systems, and Tritium Systems

## Slide 44
HNB & ICH
Areas of Technology R&D
FP Diagnostics, ECH
Major Diagnostics
Tritium System
RH Tools
R&D must be complete in time to enable integration into design and implementation for ITER needs in “Staged Approach”
By internal measures, >85% of design activity is complete : This implies major technology R&D is complete; however, some issues remain and have to be addressed.

## Slide 46
H&CD in the ITER Research Plan
*
  4-Stage Approach:
    1st Plasma: H
    PFPO-1: H and 4He
    PFPO-2: H and 4He
    FPO: D and DT
ECRH | ICRF | NBI
170 GHz (+100-110 GHz tbc) | 40-55 MHz | 870 keV H0, 1 MeV D0
20 MW (+20 MW upgrade) | 20 MW (+20 MW) | 33 MW (+16.5 MW)
 | High fusion gain, ST control, wall cleaning, modulation < 1 kHz | Bulk current drive, rotation, limited modulation
24 gyrotrons (24x0.8 MW) | 2 antennas (2x10 MW) | 2 injectors (2x16.5 MW)

## Slide 47
Status of ECH PS and RF Sources
Gyrotron: Four tubes already in manufacturing or under factory acceptance
RF-DA: first tube’s Factory Acceptance Test started in Oct. 2017; second under manufacturing
JA-DA: first two tube’s manufactured and first Factory Acceptance Test planned in April 2018;
EU-DA: CW prototype being tested in Lausanne for long pulse operation
Power Supplies: First Factory Acceptance Test has been completed in Nov. 2017; corresponding installation planned for March 2019 (B15);

## Slide 48
Status of HNB and DNB Systems
FEC*
* Front End Components
Coils
Passive Magnetic Shield
Internal components
HV Bushing
Heating Neutral Beam Injectors
Diagnostic Neutral Beam Injector

## Slide 49
Neutral Beam Test Facility : SPIDER BS
AGPS delivered and installed and tests are underway
Cooling plant of NBTF
Scaffolding installed
Plant systems commissioning with CODAS
SPIDER Beam Source : installation phase
IC-30: Start of integrated commissioning – end March 2018 (@ RFX)
Beam Dump installed

## Slide 50
Beam Source: in procurement
MITICA vessel supports inside bio shield waiting for vessel installation
MITICA 1MV Bushing: demonstrated 1MV holding
1 MV HV Deck
1 MV HV PS system
MITICA Vessel in manufacturing
Neutral Beam Test Facility : MITICA

## Slide 51
RF SOURCES (Building 15)
HV POWER SUPPLIES (Building 15)
TRANSMISSION LINES + MATCHING SYSTEM (Building 11-13-15-21)
ANTENNAS (Building 11)
Antennas: EU DA, “Build to print”, IO for the design
TL & MS: US DA, at functional specs
RF Sources : IN DA, at functional specs
HVPS: IN DA, at functional specs (44%), + IO (56%)
Status of ICH System

## Slide 52
50 different diagnostics identified for different measurement roles
Just over 100 sub-projects (in PBS55) in all
PBS55 - Diagnostics
A- Magnetics systems
B- Neutrons systems
C- Optical systems
D- Bolometry systems
E- Spectroscopy systems
F- Microwave systems
G- Operational systems
PBS55-Engineering of:
Q- Equatorial Ports
U- Upper Ports
L- Lower ports
NW- Windows
NE- Electrical Services
PBS57- IVVS
PBS58- PPTF
Status of Diagnostic System

## Slide 53
Nuclear environment means we need to mitigate transmutation, radiation damage and thermo-electric effects
Target: zero maintenance (in practice very difficult)
Quality requirements are high, in particular for assembly to the nuclear pressure vessel and vacuum vessel feedthroughs
Many interfaces (machine-diagnostics, diagnostics-diagnostics)
Engineering (remote handling capability, neutron shielding, weight)
How are we meeting these?
  Staged design, fabrication and installation approach
  Joint experiments through dedicated International Tokamak Physics Activity Diagnostic Working Group
  Dedicated R&D and development in the ITER IO-DA Teams
  Modular design and standardization
Challenges of Diagnostic System

## Slide 54
Ports for Diagnostic System
Notes: 54

## Slide 55: ITER Fuel Cycle : Tritium System

## Slide 56: Status of Fuel Cycle
Tokamak Complex Detritiation System
Receipt of Torus Cryopump
Fuel cycle has unprecedented throughput requirements
  Design and safety analysis has advanced
    Some equipment is already installed, most systems are in preliminary/final design
  High confidence that systems will work, primary questions relate to number of shots per day that can be supported
Vacuum pumping
  First torus cryopump manufacturing, testing and delivery completed
  High-throughput, tritium compatible roughing pump successfully tested
Gaseous detritiation system
  Verification testing for new, high capacity scrubber column technology completed
  Recently completed resolution of all major design issues

## Slide 57
First Torus/Cryostat Cryo-pump Fabrication
Cryo-pump Flange
Assembly of charcoal coated
panels
Thermal Shield Assembly
Cryo-pump casing preparation for e-beam welding
Cryo-pump inlet valve alignment
Completed Cryo-pump
August 2017

## Slide 58
Dual nozzle prototype at ORNL.
Due to the massive size of the ITER Tokamak components, as well as the intense neutron flux that will occur during operations, the ITER machine has required the development of cutting-edge robotics and remote handling tools, which will be used in both the assembly and operational phases.
Advanced Robotics and Remote Handling

## Slide 59
Remote Handling Technology Development
Blanket Remote Handling (Japan)
Divertor Remote Handling (EU)
Overview of the ITER Blanket RH System
Blanket module handling trials using the prototype In-Vessel Transporter (IVT) hosted by the Japanese Domestic Agency in Naka, Japan.
Overview of the ITER divertor remote handling process
Divertor cassette handling trials in the ITER Divertor Test Platform created by the European Domestic Agency in Tampere, Finland.
radial mover
transfer cask
toroidial mover
* Strong Collaboration (VR, AR, HMI…) with RACE & Industries

## Slide 60: Technology & Engineering Breakthroughs and Spinoffs

## Slide 61
Multinational Success
The single largest superconductor procurement in industrial history is completed : An eight-year campaign to produce the superconductors for ITER’s powerful magnet systems
Six ITER Members—China, Europe, Japan, Korea, Russia and the United States—have been responsible for the production of 200 kilometres (2,800 metric tons) of cable-in-conduit conductors, worth an estimated EUR 610 million.

## Slide 62
Considerable technical breakthroughs and spin-offs from the ITER Organization and Domestic Agencies activities can be observed (such as the increase in industrial capacity for the production of superconducting material). The ITER Organization and Domestic Agencies are in the process of identifying all the intellectual property related to these activities.
ITER Technologies are being developed, demonstrated, are documented, and will be available for the Members’ Fusion Programs

## Slide 63: Summary
Schedule Optimization of Tokamak Assembly and Tokamak Complex Installation with “under-pinned Critical Deliveries” showed that First Plasma in 2025
% Complete for FP installed Capital Item Components by end of December : 51.5% complete including IO assembly and installation
Technologies for ITER have been developed and are in production (for First Plasma) and nearing production (for Post-First Plasma), consistent with the needs of the “Staged Approach”
“Staged Approach” constitutes a prudent approach to investment protection and risk management : building on the successful demonstration of the previous stages till DT Operation
ITER focuses on the study of burning plasmas, both medium-pulse (400 s) and long-pulse (>1000 s): enabling scientific research on the next step of fusion science and addressing the risks related to the self-heated plasma state.