## Slide 1: Payroll Certification Pilot
FDP Update
University of California
January 6, 2014

## Slide 2: UC Riverside Update
Project Status
  Since April 2011, over 2,100 Payroll Certifications have been completed
  100% compliance (97% within 30 days of issuance)
  Estimated that over 14,000 Effort Reports would have been generated for same period

## Slide 3: UCR Update
HHS OIG on site for 4 weeks in September 2013 and one week in November 2013
Scope
  Payroll Distribution focus
  IT Security (separate OIG IT audit team; 2 weeks on-site)
  Fixed Priced Awards

## Slide 4: UCR Update
5 strata/180 payroll transactions selected:
  Charges to Expired Awards (30)
  Excess Salary (30)
  High Risk Adjustments (30)
  Administrative (30)
  Low Risk (60)

## Slide 5: UCR Update
Documentation requested for each selection:
  Support 100% of individual for year in question
    Personnel actions, payroll details across all funding sources, time records, Effort Reports/Payroll Certifications, job descriptions, teaching assignments, travel expenditures, cost transfers
  Award terms, conditions, budget detail

## Slide 6: UCR Update
18 interviews
  10 Principle Investigators
  2 Research Specialists
  1 Post Doc
  2 Graduate Students
  1 Staff Researcher
  2 Department Administrative
Interviews between 5-45 minutes long

## Slide 7: UCR Update
Feedback on documentation provided received in late November 2013
Majority of preliminary concerns raised were not specific to the payroll certification process
Supplemental documentation due 1/6/14 and will be considered prior to the issuance of the draft report
Once Draft Report issued, UCR will have 30 days to respond

## Slide 8: UC Irvine Update
IT security portion of the audit field work completed in September 2013
In November 2013, HHS OIG terminate the audit due to delays in receiving data analytics
  NSF could not use data reconciliation format UCI initially provided to run NSF analytic processes
  UCI had to re-create reconciliations for approximately 18 quarters, each quarter contained approximately 500 awards

## Slide 9: Next Steps for UC
  Due to delays with audit, UC requested an extension of pilot through December 31, 2014; however, extension only granted through 3/31/2014
HHS will issue separate audit reports to UCR and UCI

## Slide 10: Questions?
UCR Contact: Bobbi McCracken, Controller (bobbi.mccracken@ucr.edu)
UCI Contact: Bent Nielsen, Controller (bnielsen@uci.edu)